## Financial Close Tasks
Task ID | Department | Task Name | Assigned To | Country | Due Date | Status | Completion Date | Critical? | Notes | Days Remaining | Is Overdue?
TASK_001 | Accounts Payable | Match invoices with bookings | Accounts_User_4 | Netherlands | 2025-08-05 | Completed | 2025-08-04 | No |  | Done | No
TASK_002 | Accounts Receivable | Follow up on outstanding invoices | Accounts_User_3 | Netherlands | 2025-08-02 | Completed | 2025-08-01 | No |  | Done | No
TASK_003 | Accounts Receivable | Reconcile customer payments | Accounts_User_3 | Germany | 2025-08-06 | Completed | 2025-08-05 | Yes |  | Done | No
TASK_004 | Accounts Payable | Accrue supplier invoices | Accounts_User_4 | Netherlands | 2025-08-03 | Completed | 2025-08-01 | Yes |  | Done | No
TASK_005 | Accounts Payable | Match invoices with bookings | Accounts_User_3 | Germany | 2025-08-04 | Completed | 2025-08-04 | Yes |  | Done | No
TASK_006 | General Ledger | Post payroll journal entries | General_User_5 | Germany | 2025-08-03 | In Progress |  | No |  | -17 | Yes
TASK_007 | Tax & Compliance | Review intercompany charges | Tax_User_1 | Germany | 2025-08-06 | Completed | 2025-08-04 | Yes |  | Done | No
TASK_008 | Tax & Compliance | Review intercompany charges | Tax_User_4 | Germany | 2025-08-04 | Completed | 2025-08-04 | No |  | Done | No
TASK_009 | Accounts Receivable | Reconcile customer payments | Accounts_User_1 | Netherlands | 2025-08-02 | Completed | 2025-08-01 | No |  | Done | No
TASK_010 | Accounts Payable | Accrue supplier invoices | Accounts_User_3 | Netherlands | 2025-08-06 | Completed | 2025-08-06 | No |  | Done | No
TASK_011 | Accounts Payable | Match invoices with bookings | Accounts_User_3 | Germany | 2025-08-04 | Completed | 2025-08-04 | No |  | Done | No
TASK_012 | Accounts Payable | Verify travel agent bills | Accounts_User_4 | Netherlands | 2025-08-06 | Completed | 2025-08-05 | No |  | Done | No
TASK_013 | General Ledger | Perform FX revaluation | General_User_4 | Netherlands | 2025-08-05 | Completed | 2025-08-05 | No |  | Done | No
TASK_014 | Accounts Payable | Match invoices with bookings | Accounts_User_3 | Germany | 2025-08-05 | Completed | 2025-08-05 | Yes |  | Done | No
TASK_015 | Accounts Payable | Accrue supplier invoices | Accounts_User_5 | Germany | 2025-08-04 | Completed | 2025-08-04 | Yes |  | Done | No
TASK_016 | Accounts Payable | Accrue supplier invoices | Accounts_User_3 | Germany | 2025-08-05 | Blocked |  | No |  | -15 | Yes
TASK_017 | Accounts Receivable | Reconcile customer payments | Accounts_User_1 | Germany | 2025-08-06 | Blocked |  | No |  | -14 | Yes
TASK_018 | Accounts Payable | Accrue supplier invoices | Accounts_User_5 | Germany | 2025-08-03 | Completed | 2025-08-03 | Yes |  | Done | No
TASK_019 | Tax & Compliance | Review intercompany charges | Tax_User_3 | Netherlands | 2025-08-03 | Completed | 2025-08-03 | No |  | Done | No
TASK_020 | General Ledger | Clear suspense accounts | General_User_1 | Netherlands | 2025-08-06 | Completed | 2025-08-06 | Yes |  | Done | No
TASK_021 | General Ledger | Clear suspense accounts | General_User_5 | Netherlands | 2025-08-05 | Completed | 2025-08-05 | No |  | Done | No
TASK_022 | FP&A | Submit financial results to HQ | FP&A_User_5 | Germany | 2025-08-04 | Completed | 2025-08-04 | Yes |  | Done | No
TASK_023 | General Ledger | Post payroll journal entries | General_User_2 | Germany | 2025-08-05 | Completed | 2025-08-05 | No |  | Done | No
TASK_024 | Tax & Compliance | Book VAT entries | Tax_User_4 | Germany | 2025-08-06 | Completed | 2025-08-06 | No |  | Done | No
TASK_025 | Tax & Compliance | Prepare statutory tax report | Tax_User_5 | Germany | 2025-08-03 | Completed | 2025-08-01 | No |  | Done | No
TASK_026 | Accounts Payable | Match invoices with bookings | Accounts_User_3 | Netherlands | 2025-08-06 | Completed | 2025-08-06 | No |  | Done | No
TASK_027 | General Ledger | Clear suspense accounts | General_User_5 | Netherlands | 2025-08-04 | Completed | 2025-08-01 | Yes |  | Done | No
TASK_028 | FP&A | Submit financial results to HQ | FP&A_User_1 | Netherlands | 2025-08-06 | In Progress |  | No |  | -14 | Yes
TASK_029 | Tax & Compliance | Prepare statutory tax report | Tax_User_3 | Germany | 2025-08-03 | Blocked |  | No |  | -17 | Yes
TASK_030 | General Ledger | Perform FX revaluation | General_User_5 | Germany | 2025-08-05 | Completed | 2025-08-05 | Yes |  | Done | No
TASK_031 | General Ledger | Clear suspense accounts | General_User_1 | Germany | 2025-08-06 | Completed | 2025-08-06 | No |  | Done | No
TASK_032 | Accounts Receivable | Confirm revenue recognition | Accounts_User_3 | Germany | 2025-08-03 | Completed | 2025-08-01 | Yes |  | Done | No
TASK_033 | FP&A | Validate monthly P&L | FP&A_User_3 | Netherlands | 2025-08-04 | Completed | 2025-08-04 | Yes |  | Done | No
TASK_034 | FP&A | Submit financial results to HQ | FP&A_User_1 | Germany | 2025-08-05 | Completed | 2025-08-05 | Yes |  | Done | No
TASK_035 | General Ledger | Perform FX revaluation | General_User_2 | Netherlands | 2025-08-02 | In Progress |  | No |  | -18 | Yes
TASK_036 | FP&A | Update monthly forecast | FP&A_User_1 | Netherlands | 2025-08-06 | Completed | 2025-08-06 | Yes |  | Done | No
TASK_037 | General Ledger | Post payroll journal entries | General_User_4 | Netherlands | 2025-08-05 | Completed | 2025-08-05 | Yes |  | Done | No
TASK_038 | Accounts Payable | Verify travel agent bills | Accounts_User_3 | Netherlands | 2025-08-06 | Completed | 2025-08-06 | No |  | Done | No
TASK_039 | Tax & Compliance | Review intercompany charges | Tax_User_4 | Netherlands | 2025-08-06 | In Progress |  | No |  | -14 | Yes
TASK_040 | Tax & Compliance | Book VAT entries | Tax_User_5 | Germany | 2025-08-05 | In Progress |  | No |  | -15 | Yes
8
Formulas:
Days Remaining = IF([Status]="Completed","Done",[Due Date]-TODAY())
Is Overdue? = IF(AND([Status]<>"Completed",[Due Date]<TODAY()),"Yes","No")

## Pivot Tables
Status | Count of Task ID | Department | Count of Task ID | Uncompleted Tasks |  |  |  | Unfinished Tasks |  |  |  | Row Labels | Count of Task ID
Blocked | 3 | Accounts Payable | 12 | Departments | Blocked | In Progress | Grand Total | Users | Blocked | In Progress | Grand Total | Germany | 21
Completed | 32 | Accounts Receivable | 5 | Accounts Payable | 1 |  | 1 | Accounts_User_1 | 1 |  | 1 | Netherlands | 19
In Progress | 5 | FP&A | 5 | Accounts Receivable | 1 |  | 1 | Accounts_User_3 | 1 |  | 1 | Grand Total | 40
Grand Total | 40 | General Ledger | 10 | FP&A |  | 1 | 1 | FP&A_User_1 |  | 1 | 1
|  | Tax & Compliance | 8 | General Ledger |  | 2 | 2 | General_User_2 |  | 1 | 1
|  | Grand Total | 40 | Tax & Compliance | 1 | 2 | 3 | General_User_5 |  | 1 | 1
|  |  |  | Grand Total | 3 | 5 | 8 | Tax_User_3 | 1 |  | 1
[8 empty] | Tax_User_4 |  | 1 | 1
[8 empty] | Tax_User_5 |  | 1 | 1
[8 empty] | Grand Total | 3 | 5 | 8

## Dashboard
Financial Close Dashboard – August 2025
Completed Tasks | Overdue Tasks | Number of all Tasks
32 | 8 | 40
Key Insights - 8 Tasks are overdue which were moslty in Gerenal Ledger and Tax&Compliance. - All 16 critical taks were completed on time which shows a good indication at strong prioritization. - Blocked tasks were monstly linked to manual invoice matching in AP. Recommendations 1. Automate supplier invoice matching using MS Dynamics to reduce manual work. 2. Implement daily task monitoring during close week with automated alerts. 3. Standardize reconciliation templates across countries to streamline reviews.